AI Technical Program Manager — UST

Week 1 · Participant Workbook

Your working file for Days 2 and 3. Fill it in as you go, then submit this same file.

For: every participant. Save your own copy before you start typing.

File name for your copy: UST_AITPM_Week1_Workbook_<your candidate id>

Used in: Day 2 (M1 and M2) and Day 3 (M3 and M4). Instructions, hints and examples are in the Lab Kit; this file holds only the forms.

# Before you begin: why this document exists

### Why this step is needed

Your Week 1 work is scored by an evaluation agent that reads your submission and must quote your own words for every score. If your findings, owners, checklist and readiness statement are spread across several files, or written in a format the evaluator cannot read, you lose marks you have earned. One workbook keeps everything in one place, in the right order.

### What exactly happens in this step

You fill in six parts over the two lab sessions: the cover block, the Findings Log (M1, Day 2), the governance frame (M2, Day 2), Release-Readiness Checklist v1 (M3, Day 3), the readiness statement to the sponsor and your assumptions (M4, Day 3). At the end of Day 3 you check it and submit this file.

### The purpose of what is being done

To let you spend the lab thinking instead of formatting, and to make sure the evaluator finds every piece of evidence for your score exactly where it expects it.

### Which part of the programme architecture this builds

This is the submission file for Week 1, whose work product is Release-Readiness Checklist v1. The same structure (findings, frame, checklist, statement) is reused in later weeks, and your Checklist v1 becomes the first layer of your Week 6 capstone.

# How to use this workbook

| Do | Do not |
| --- | --- |
| Type directly into the tables. Add rows wherever you need them (in Word: right-click a row, then Insert). | Paste screenshots, images or diagrams instead of text. The evaluator can only score words it can quote. |
| Delete the grey example rows before you submit. | Write "TBD", a team name, or a role without a person where an owner is asked for. |
| Use only the people in the Scenario Pack org chart (Part A3). | Invent people, numbers or documents that the case does not contain. If you must assume something, record it in Part 6. |
| Save often, and keep a copy somewhere you can open tomorrow. | Polish the formatting. Polish earns nothing; specific, checkable content earns everything. |

# Part 1 · Cover block

| Field | Your entry |
| --- | --- |
| Candidate id | U57626 Suraj Radhakrishnan |
| Week | Week 1 · Release-Readiness Checklist v1 |
| Domain track used | Kestrel Health Network ( Healthcare) |
| Did you use your own live project instead of the case? | No |
| AI tool(s) used | Any platform. Claude Opus 5.5 and Co-Pilot : GPT 5.6 |
| Day 2 partner (M1 and M2) |  |
| Day 3 peer reviewer (M4) |  |
| Attempt number | 1 / 2 / 3 |
| Date submitted | 30-Oct-26 |

# Part 2 · Findings Log (M1, Day 2)

Record every weakness in checklist v0.9 that would stop a careful stranger trusting that Lumen is ready. Aim for 12 to 20 findings, with at least one for each of the five dimensions. See the Lab Kit, Section 2.

Category: use one or more of Dimension gap · Ownership · AI control · Stage gate · Evidence · Contradiction. Evidence reference: the Scenario Pack part and item, for example "Part C1, report footer" or "Part C2, 4 Nov message".

| # | v0.9 item(s) | Finding (what is wrong) | Category | Why it matters (for the sponsor) | Evidence reference | What v1 must contain instead |
| --- | --- | --- | --- | --- | --- | --- |
| F1 | #11 | "Clinical safety case signed" is Corvid's hazard log v2, signed by Corvid's CSO for CorvidBench deployments. Kestrel has no safety case of its own; the owner is the Delivery Lead, and the Kestrel CSO has "not been asked to review it". No hazards for automated replies, mixed-language messages or nurse-queue capacity. | Clinical; Compliance (CSS-1); Ownership | Beacon would go live with no one at Kestrel accountable for its clinical safety, breaching CSS-1. The three hazards most specific to Kestrel are not assessed at all. | E7; E2; A4 CSS-1; A5 Spec | Review stage, Pilot gate: a Kestrel clinical safety case and hazard log owned and signed by Dr. Helen Mathews, covering auto-replies, mixed-language under-triage, nurse-queue capacity and patient follow-up replies. Corvid's log listed as an input only. |
| F2 | #10; appendix threshold note | Checklist says threshold 0.80; live config is 0.72, lowered on 25 Nov by Imran "to reduce nurse queue" with no re-evaluation and no CSO approval. The appendix lets "Engineering" tune it operationally. "Eval numbers will be basically the same" is a claim, not evidence. | AI control (confidence threshold); Compliance (AIP-2) | A lower threshold sends more messages to patients and clinics without a nurse. The under-triage rate at 0.72 is unknown, and the change breaches AIP-2. | E3; E4 26 Nov; E1; A4 AIP-2 | Build stage, Pilot gate: a threshold row stating the value, the build and model evaluated, and the Kestrel under-triage rate at that value (overall and by language); CSO approval; rule "no change without re-evaluation and CSO approval"; appendix note removed. Owner: Dr. Farah Siddiqui. Approver: Dr. Helen Mathews. |
| F3 | #9 | "Model validated (96% accuracy)" is Corvid's own benchmark on 48,000 US/UK primary-care messages, not Kestrel patients. Accuracy is the wrong measure; under-triage is the safety-critical one. On Kestrel data accuracy is 0.93 and under-triage 2.1%. | Clinical; AI control | The headline number describes a different population and hides the measure that harms patients: urgent cases sent to self-care. | E2; E1 | Build stage, Pilot gate: validation on Kestrel data with an agreed under-triage acceptance limit, overall and per language subgroup, reviewed by the CSO. Owner: Dr. Farah Siddiqui. Approver: Dr. Helen Mathews. |
| F4 | #8, #9, #10 | Evidence does not match the release. ev-118 ran on build 1.4.0, threshold 0.80, corvid-med-3.2, with clinical review "pending". The release is build 1.4.2, 0.72, floating alias. The 1.4.2 regression suite "does not include the model evaluation set". | Technical; AI control; Stage gate (Build) | Nobody has measured how the exact system going live on 14 Dec triages patients. "Regression green" says the code runs, not that triage is safe. | E1 footer; E3; E4 27 Nov (V. Osei) | Build stage, Pilot gate: model evaluation set re-run on the release candidate (build, model version, prompt version and threshold recorded) and included in the release test strategy. Owner: Victor Osei. Approver: Dr. Helen Mathews. |
| F5 | #27 | "Vendor model-change process agreed" is only the contract's 14-day notice. Kestrel chose the floating alias corvid-med-latest, which Corvid switches to 3.3 on 15 Dec, the day after go-live. "Non-material, no action required" is the supplier's claim; AIP-2 requires re-evaluation and CSO approval for any model change. | AI control; Technical; Compliance (AIP-2) | The model that was evaluated will be swapped silently on day 2 of the pilot. Kestrel loses control of its own clinical output. | E3; E4 30 Nov; E8 CTR-311 cl. 9.4; A4 AIP-2 | Plan stage, Pilot gate: model pinned to an evaluated version (pinned versions available at extra cost); any version change goes through re-evaluation on Kestrel data and CSO approval before use. Owner: Imran Qureshi (config). Budget approver: Marcus Bell. Clinical approver: Dr. Helen Mathews. |
| F6 | #18 | R-17 shows "accepted", but Neha accepted it "on behalf of delivery so we stay green". AIP-2 allows only the CMO or CSO to accept clinical risk, in writing, with a review date. Mixed-language under-triage is 6.8% vs 1.6% for English-only. | Compliance (AIP-2); Clinical; Ownership | The acceptance is invalid. Patients writing in Hindi, Marathi or mixed script are four times as likely to have an urgent case missed, and nobody with authority has decided that is acceptable. | E4 5 Dec, 7 Dec; E1; A4 AIP-2 | Review stage, Pilot gate: R-17 either mitigated (all mixed-language or transliterated messages to the nurse queue, with evidence) or accepted in writing by Dr. Anjali Rao or Dr. Helen Mathews with a review date; register records the correct name. |
| F7 | #17, #24 | "Urgent → nurse queue, 30-minute response" cannot be met: 2 night nurses cover both sites plus the ward phone line, and the urgent queue peaks at ~25 cases (~75 minutes to clear). The HITL trigger names only urgent cases, not low-confidence or mixed-language ones. Training is "assigned"; only 11 of 29 nurses (38%) have completed it. | AI control (HITL); Operational | The safety net Beacon relies on would be overloaded exactly when risk is highest, and staffed partly by untrained nurses. | E4 1 Dec; E8 item 24; E1 (31% to queue) | Release stage, Pilot gate: a HITL row with triggers (Emergency/Urgent, confidence below threshold, mixed-language, patient follow-up reply), a response target backed by a staffing calculation, an escalation route on queue breach, and 100% training completion for pilot-site nurses. Owner: Priyanka Das. Approver: Dr. Anjali Rao. |
| F8 | #19, #20 | The "Beacon Drift" dashboard uses a CorvidBench baseline, not Kestrel's. No under-triage measure exists in production and no clinician sampling of auto-routed messages is scheduled. Alerts go to a 14-person chat channel on no on-call rota; Kavya's rota is paged only for infrastructure alerts. | AI control (drift monitor); Operational; Ownership | If Beacon starts missing urgent patients, nothing measures it, nothing alerts on it, and nobody is called. | E5 | Release stage, Pilot gate: a drift-monitor row with measures (category mix, mean confidence, auto-route rate, language mix, under-triage from a scheduled clinician sample), Kestrel baseline from ev-118, tolerance bands, paged alert, named responder. Owner: Kavya Nair. Clinical sampling owner: Priyanka Das. |
| F9 | #21 | "Audit logging enabled" logs only message_id, category and confidence: no rationale, model or prompt version, threshold, routing decision, reply text or nurse override. | Data & Security; Compliance (RP-1) | Kestrel could not reconstruct why a patient was routed or what they were told, so it could not answer an incident investigation or complaint. | E3; A4 RP-1 | Release stage, Pilot gate: audit fields covering every decision about a patient: input reference, category, confidence, rationale, model version, prompt version, threshold, route taken, reply text sent, nurse override. Owner: Kavya Nair. Approver: Owen Fletcher. |
| F10 | #22 | Retention is 365 days; RP-1 requires 8 years for patient communications and care decisions. The owner is "Platform / Nursing (joint)", which is not a person. | Compliance (RP-1); Ownership | Kestrel would destroy clinical records it is required to keep, and nobody is accountable. | E3; A4 RP-1; A3 | Release stage, Pilot gate: retention of 8 years for decision logs and patient messages, verified in config. Owner: Kavya Nair. Approver: Grace Liu. |
| F11 | #23 | Rollback rehearsed only for the app container (1.4.2 → 1.3.9). The runbook does not cover model version, prompt version, threshold, or a kill switch sending all messages to nurses. The owner, Tobias, leaves on 18 Dec. | Technical; Operational; Ownership | If Beacon misbehaves, the change most likely to cause it (the model) cannot be undone, and there is no rehearsed way to switch Beacon off safely. | E6; A3 | Release stage, Pilot gate: rollback rehearsed for app, model pin, prompt and threshold, plus a rehearsed kill switch to full manual triage with nurse capacity for it. Owner: Kavya Nair. Approver: Priyanka Das (manual-triage capacity). |
| F12 | #8, #9, #4, #15, #23, #22; appendix ownership note | Owners who cannot be accountable: Jonas Weber left on 16 Oct; Tobias Grant is a contractor leaving 18 Dec, before the network rollout, yet "technical items" are his "until handover"; "Platform / Nursing (joint)" is a team. | Ownership | The 11 Jan rollout would run with owners who no longer work at Kestrel and no recorded handover. | A3; Part B appendix | All gates: every row owned by a current Kestrel person from A3, e.g. Victor Osei (test), Kavya Nair (platform, load, rollback), Imran Qureshi (architecture) after a recorded handover from Tobias before 18 Dec. |
| F13 | #3, #4; Intent gate | Scope changed by team-channel decision on 9 Oct (portal messages, auto-replies), but intent.md still covers referral letters only. ADR-009 (21 Sept) predates the change, with no later architecture review. Intent and Spec gates were "approved" against artefacts describing a different product. | Stage gate (Intent/Spec); Technical | The two riskiest capabilities, patient-written messages and automated replies, were never formally intended, designed or reviewed. | A5 Intent, Spec; E8 item 4 | Intent and Spec stages, Pilot gate: intent.md updated to current scope and approved by Dr. Anjali Rao, plus an architecture review covering portal, auto-reply and MedLink flows. Owner: Imran Qureshi. Approver: Rahul Menon. |
| F14 | #6 | "Feature plans complete" is untrue: 9 of 11 exist. The two missing, "automated reply drafting" and "threshold tuning", called "small config features", directly decide what a patient receives. | Stage gate (Plan); Clinical | The highest-risk changes skipped planning entirely, which is how the 0.72 change happened unreviewed. | A5 Plan | Plan stage, Pilot gate: plans for all 11 features, with the auto-reply and threshold plans including a clinical review step. Owner: Imran Qureshi. Approver: Dr. Helen Mathews. |
| F15 | #12 | "87 of 87 PRs approved", but 12 were approved by Imran, who wrote the prompts the coding agent used to produce them. Review-agent reports are not independent human review. | Technical; Stage gate (Review) | About one in seven changes was effectively marked by its author: no independent check on agent-written clinical code. | A5 Review | Review stage, Pilot gate: the 12 self-approved PRs re-reviewed by a human who did not write the prompts (e.g. Tobias Grant before 18 Dec), plus a standing rule that reviewer ≠ prompt author. Owner: Imran Qureshi. Approver: Victor Osei. |
| F16 | #14 | "DPIA approved" refers to DPIA v1 (August), which covers referral letters only. The DPO says an addendum is needed "before patient messages are processed". | Data & Security; Compliance | Processing patient portal messages without a valid DPIA is a data-protection breach on day one. | E4 2 Dec | Review stage, Pilot gate: a DPIA addendum covering portal messages and automated replies, approved by Grace Liu. |
| F17 | #26, #16 | "AI disclosure approved" is a draft with Legal, English only, owned by Marcus. Self-care replies read at grade 11 vs PCS-3's grade 8 limit. Accessibility is "N/A – backend service", yet Beacon writes directly to patients. | Clinical; Compliance (PCS-3) | Patients would receive AI advice they may not understand, possibly not in their language, without being told a machine drafted it. | E8 item 26; E1 (grade 11); A4 PCS-3 | Release stage, Pilot gate: disclosure wording approved in English, Hindi and Marathi; reply sample at grade 8 or below in all three languages; accessibility review of patient-facing replies. Owner: Neha Sharma. Approvers: Owen Fletcher (policy), Dr. Helen Mathews (clinical content). |
| F18 | #25 | "Contact centre briefed" was an email with release notes: no call scripts and no route for a patient who replies "it's getting worse". Such replies land in the general inbox, answered within 48 hours. | Operational; Clinical | A patient wrongly given self-care advice who then deteriorates could wait two days for a human. This is the most direct patient-harm path in the evidence. | E4 3 Dec; E8 item 25 | Release stage, Pilot gate: replies to Beacon messages routed to the nurse queue (not the general inbox) and tested end to end, plus call scripts with escalation wording. Owners: Sunil Bhat (scripts), Priyanka Das (routing). |
| F19 | #30; appendix gate notes | All five stage gates "approved" by Neha Sharma on the same day (2 Dec): the Delivery Lead approving her own work, with no evidence attached. The appendix says the network rollout "proceeds per Rollout plan v2" after the pilot passes: no network phase gate. | Stage gate; Ownership | The ticks are a sign-off, not evidence. Nine hospitals would go live on 11 Jan with no check that the pilot was actually safe. | Part B appendix; A5 | Every gate approved by the Accountable owner for its dimension, not the Delivery Lead, against attached evidence. A separate Network gate before 11 Jan requires pilot under-triage sampling results, drift baseline confirmed, model-change decision made and Tobias's handover done. Approver: Dr. Anjali Rao. |
| F20 | #15, #28 | Load test passed at 3× pilot volume: pilot scale only. Nine hospitals exceeds 3× the two pilot sites, and the test measures latency, not nurse capacity. The owner leaves on 18 Dec. "Rollout plan v2 ✓" is ticked before the pilot has produced any evidence. | Technical; Operational; Stage gate (phase) | The pilot gate is being used to approve the network rollout, which it was never sized for. | Part B #15, #28; A3 | Network gate: load test at network volume, nurse-capacity calculation per site, rollout plan revised after pilot results. Owners: Kavya Nair (load), Priyanka Das (capacity). Approver: Dr. Anjali Rao. |
| Dimension coverage: Clinical (F1, F3, F6, F14, F17, F18) · Technical (F4, F5, F11, F13, F15, F20) · Data & Security (F9, F16) · Compliance (F1, F2, F5, F6, F9, F10, F16, F17) · Operational (F7, F8, F11, F18, F20). |  |  |  |  |  |  |

# Part 3 · Governance frame (M2, Day 2)

Decide the structure of your checklist before you write it. See the Lab Kit, Section 3.

## 3a. Who owns each dimension?

Exactly one Accountable person per dimension, by name, from the org chart. One person may own two dimensions; one dimension never has two Accountables. Test each with the Saturday question: if this fails on go-live weekend, is this the person whose phone rings?

| Dimension | Accountable (one named person) | Responsible | Consulted | Informed | Why this person (one sentence) |
| --- | --- | --- | --- | --- | --- |
| Business | Dr. Anjali Rao | Marcus Bell (business case, budget incl. pinned-model cost); Neha Sharma (delivery plan, scope record) | Dr. Helen Mathews; Priyanka Das | Owen Fletcher; Kavya Nair | As sponsor and Chief Medical Officer she chairs the Go/No-Go, is one of only two people AIP-2 allows to accept clinical risk, and is the person who must decide to stop the pilot. |
| Technical | Imran Qureshi | Tobias Grant (architecture review and handover, until 18 Dec only); Rahul Menon (security testing) | Kavya Nair; Victor Osei | Neha Sharma; Dr. Farah Siddiqui | He runs the agentic build, approves PRs and controls triage-config.yaml, so a broken build, prompt or config on go-live weekend is his to fix; Tobias cannot be Accountable because he leaves on 18 Dec. |
| Quality | Victor Osei | Dr. Farah Siddiqui (Kestrel evaluation set, under-triage measures); Imran Qureshi (CI including eval set) | Dr. Helen Mathews; Priyanka Das | Neha Sharma; Dr. Anjali Rao | He has owned the test strategy since November and is the only current QA owner; Jonas Weber, the owner in v0.9, left on 16 Oct. |
| Governance | Dr. Helen Mathews | Owen Fletcher (AIP-2, risk register); Grace Liu (DPIA addendum); Rahul Menon (security sign-off) | Dr. Anjali Rao; Dr. Farah Siddiqui | Marcus Bell; Neha Sharma | CSS-1 makes the Kestrel CSO the owner and signatory of the safety case, and AIP-2 requires her approval for any model, prompt or threshold change. |
| Operational | Kavya Nair | Priyanka Das (nurse queue, HITL staffing, training, clinician sampling); Sunil Bhat (contact-centre scripts, follow-up routing) | Imran Qureshi; Dr. Helen Mathews | Dr. Anjali Rao; Neha Sharma | She owns hosting, monitoring, alerting, rollback and the on-call rota, so when a drift alert or outage fires on Saturday hers is the phone that is paged. |

## 3b. Where is each dimension checked? (stage-gate map)

In each cell where a gate exists, write who approves crossing it and the artefact they look at, for example "Approver: name · Artefact: signed eval report". Leave the cell empty where there is no gate. Use all six stages; at least three dimensions should have gates at more than one stage.

| Dimension | Intent | Spec | Plan | Build | Review | Deploy |
| --- | --- | --- | --- | --- | --- | --- |
| Business | Approver: Dr. Anjali Rao · Artefact: intent.md v2 covering referral letters, portal messages and automated replies (9 Oct scope change formally recorded) |  | Approver: Marcus Bell · Artefact: costed plan incl. pinned-model cost (CTR-311 cl. 9.4) and a pilot-learning window before network rollout |  |  | Approver: Dr. Anjali Rao · Artefact: Checklist v1 with all pilot-gate rows Met, recorded in Go/No-Go minutes; for network gate, the pilot results report |
| Technical |  | Approver: Rahul Menon · Artefact: architecture review addendum to ADR-009 for portal, auto-reply and MedLink data flows | Approver: Imran Qureshi · Artefact: plans for 11 of 11 features, incl. auto-reply drafting and threshold tuning | Approver: Imran Qureshi · Artefact: release manifest of build 1.4.x with pinned model version, prompt version and threshold | Approver: Rahul Menon · Artefact: PT-2026-77 retest report and independent re-review of the 12 self-approved PRs (reviewer ≠ prompt author) |  |
| Quality |  | Approver: Victor Osei · Artefact: test strategy with acceptance criteria incl. under-triage limits overall and per language |  | Approver: Victor Osei · Artefact: signed evaluation report on the release candidate (build, model, prompt, threshold) and CI run including the eval set | Approver: Victor Osei · Artefact: reply test pack: reading level grade 8 or below and language check (EN/HI/MR) per PCS-3 | Approver: Victor Osei · Artefact: clinician sampling results of auto-routed pilot messages (network gate) |
| Governance | Approver: Owen Fletcher · Artefact: AIP-2 classification and risk-register entries for the October scope | Approver: Dr. Helen Mathews · Artefact: Kestrel hazard log v1 replacing the copied Corvid section in spec.md | Approver: Grace Liu · Artefact: DPIA addendum for portal messages and automated replies |  | Approver: Dr. Helen Mathews · Artefact: signed Kestrel clinical safety case, CSO approval of threshold, written R-17 decision with review date | Approver: Dr. Helen Mathews · Artefact: change-control record: no model, prompt or threshold change without re-evaluation and CSO approval (incl. Corvid 15 Dec change) |
| Operational |  |  | Approver: Priyanka Das · Artefact: nurse-capacity plan for the 7–10 pm peak (~25 urgent cases) with a staffed response target |  | Approver: Kavya Nair · Artefact: rehearsal record for rollback of app, model, prompt and threshold plus kill switch to full manual triage | Approver: Kavya Nair · Artefact: drift monitor live on Kestrel baseline with paged on-call responder; training completion 100%; follow-up reply route tested |

3c. What must be true at the pilot gate versus the network gate

The network gate is a separate decision, not an automatic consequence of passing the pilot gate (replaces the v0.9 appendix note). Each Accountable signs their row; Dr. Anjali Rao takes the decision at each gate.

| Dimension | Pilot gate · Kestrel Riverside and Hillcrest · 14 Dec 2026 | Network gate · all nine hospitals · 11 Jan 2027 | Sign-off (pilot / network) |
| --- | --- | --- | --- |
| Business | intent.md v2 approved by Dr. Anjali Rao; pilot success and stop criteria written down (under-triage limit, nurse response time); Go/No-Go decision and any conditions recorded in minutes. | Pilot results report against those criteria; Dr. Anjali Rao signs a separate network Go/No-Go; Marcus Bell confirms budget for a pinned model across nine hospitals. | Dr. Anjali Rao / Dr. Anjali Rao |
| Technical | Model pinned to the evaluated version (no corvid-med-latest); live config matches the evaluated build, prompt and threshold; 12 self-approved PRs independently re-reviewed; architecture review of portal and auto-reply flows done; penetration test passed (already met). | Tobias Grant's handover to Imran Qureshi recorded before 18 Dec; load test at nine-hospital volume; any move to corvid-med-3.3 re-evaluated and approved first. | Imran Qureshi / Imran Qureshi |
| Quality | Kestrel evaluation re-run on the release candidate; under-triage within the agreed limit overall and per language, or all mixed-language messages routed to nurses; self-care replies at grade 8 or below in English, Hindi and Marathi. | Clinician sampling of pilot auto-routed messages shows under-triage within the limit; evaluation refreshed with pilot data and the language mix of the other seven sites. | Victor Osei / Victor Osei |
| Governance | Kestrel clinical safety case and hazard log signed by Dr. Helen Mathews; CSO approval of the threshold in use; R-17 mitigated or accepted in writing by Dr. Anjali Rao or Dr. Helen Mathews with a review date; DPIA addendum approved by Grace Liu; AI disclosure approved in three languages; retention set to 8 years. | Safety case updated with pilot incidents and near-misses; R-17 re-decided at its review date; change control shown to work on any model change; risk register updated by Owen Fletcher. | Dr. Helen Mathews / Dr. Helen Mathews |
| Operational | HITL triggers include low confidence, mixed-language and patient follow-up replies; staffed urgent response target for the night peak; 100% of pilot-site nurses trained; "it's getting worse" replies go to the nurse queue, not the 48-hour inbox; contact-centre scripts issued; drift monitor on a Kestrel baseline with a paged responder; rollback and kill switch rehearsed; audit fields complete. | Staffing plan and response targets for each of the nine sites; training complete at all sites; drift baseline reset from pilot production data; on-call rota covering nine sites. | Kavya Nair / Kavya Nair |

# Part 4 · Release-Readiness Checklist v1 (M3, Day 3)

This is the scored work product. Write 20 to 35 rows. Every row needs all nine columns filled. See the Lab Kit, Sections 4 and 8 (worked example).

## 4a. Header block

| Field | Your entry |
| --- | --- |
| Product / release | Beacon build 1.4.2 — AI-assisted patient triage (GP referral letters and patient-portal messages), Kestrel Health Network |
| Checklist version | v1 · 8 December 2026 · author: [candidate id] · supersedes Beacon Release Readiness v0.9 |
| Governance structure | Every criterion answers: what is enforced · what evidence exists · where it is logged · who approves. Each row states its stage (Intent → Deploy) and the phase it gates: Pilot (Riverside and Hillcrest, 14 Dec 2026) or Network (nine hospitals, 11 Jan 2027). |
| Accountable owners by dimension | Business: Dr. Anjali Rao · Technical: Imran Qureshi · Quality: Victor Osei · Governance: Dr. Helen Mathews · Operational: Kavya Nair |
| Purpose of the 10 Dec Go/No-Go meeting | To decide whether Beacon may go live at the two pilot sites on 14 Dec, which it may only if every Pilot-phase row is Met or covered by a named, dated condition the sponsor accepts; the network rollout is decided separately at the Network gate before 11 Jan. |

## 4b. Criteria

Write the three AI-control rows first (Day 3 starts with a 10-minute sprint on them). Each must state: AI-01 Confidence threshold: the metric · the number · where the number came from (which data) · a named owner · what happens below it AI-02 Human-in-the-loop trigger: the condition that sends a case to a person · the named role that receives it · the time limit AI-03 Model drift monitor: what is measured · the baseline · the acceptable band · where the alert goes · who responds · the action on a breach

| ID | Stage | Phase | Dimension | Criterion (a checkable question) | Evidence required | Where logged | Accountable owner (named) | Approver | Status at 8 Dec + basis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AI-01 | Build | Pilot | Governance | Confidence threshold: Metric: Beacon's confidence score for the assigned category; Routine and Self-care messages are auto-routed only at or above the threshold. Number: 0.80, the only value evaluated on Kestrel data (ev-118, 3,000 Kestrel messages vs nurse consensus), re-confirmed on the release configuration. Below it: the message goes to the triage nurse queue. Changes only after re-evaluation on Kestrel data and CSO approval (AIP-2); the v0.9 note allowing Engineering to tune it is withdrawn. | Evaluation report on release build showing under-triage at 0.80; CSO approval memo; triage-config.yaml showing 0.80 | beacon/triage-config.yaml; evaluation register; CSO approvals log | Dr. Farah Siddiqui | Dr. Helen Mathews | Not met — config is 0.72 since 25 Nov (E3), lowered by I. Qureshi without re-evaluation or CSO approval (E4 26 Nov); ev-118 ran on build 1.4.0 and its CSO review is pending (E1). |
| AI-02 | Deploy | Pilot | Operational | Human-in-the-loop trigger: Condition: a message goes to a person if any of these hold: category Emergency or Urgent; confidence below 0.80; mixed-language or transliterated text (R-17 mitigation); any patient reply to a Beacon automated message; Beacon error or timeout. Receiver: the on-shift triage nurse at the patient's pilot site. Time limit: Emergency within 15 minutes, Urgent within 30 minutes, including the 7–10 pm peak; any breach escalates to the Head of Nursing. | Routing test results for all five triggers; night-peak staffing rota showing capacity to meet 30 minutes for ~25 urgent cases; escalation procedure | Test log in repo; nursing rota; nursing SOP | Priyanka Das | Dr. Helen Mathews | Not met — only Urgent/Emergency and low-confidence routing exist; 2 night nurses need ~75 minutes to clear the peak vs 30 (E4 1 Dec); patient replies land in a 48-hour inbox (E4 3 Dec); no mixed-language trigger (E1, R-17). |
| AI-03 | Deploy | Pilot | Operational | Model drift monitor: Measured: weekly under-triage rate from clinician review of a random sample of auto-routed messages at each pilot site; daily category mix, mean confidence, auto-route rate and share of mixed-language messages. Baseline: Kestrel evaluation of the release configuration (ev-118 re-run), not CorvidBench. Band: under-triage within the CSO-approved limit (no worse than the evaluated 2.1%); auto-route rate within ±5 points of baseline; any category share within ±5 points. Alert: paged through the platform on-call rota, not a chat channel. Responder: Kavya Nair's platform on-call, with clinical review by the CSO. Action on breach: switch off auto-routing so every message goes to nurses, within 1 hour; resume only with CSO approval. | Dashboard with Kestrel baseline loaded; scheduled clinician sampling; paging test record; breach runbook | Grafana "Beacon Drift"; on-call paging system; runbook | Kavya Nair | Dr. Helen Mathews | Not met — baseline is CorvidBench; no production under-triage measure and no sampling scheduled; alerts post to #beacon-alerts, which is on no on-call rota (E5). |
| RR-04 | Intent | Pilot | Business | Does intent.md describe the current scope (referral letters, portal messages and automated replies), and is it approved by the sponsor? | intent.md v2 with sponsor approval | beacon/intent.md; Go/No-Go minutes | Neha Sharma | Dr. Anjali Rao | Not met — intent.md covers referral letters only; portal messages and auto-replies were added by a team-channel decision on 9 Oct (A5). |
| RR-05 | Intent | Pilot | Business | Is the business case approved? | Board paper | Board papers, August | Marcus Bell | Dr. Anjali Rao | Met — board paper, August (v0.9 #1). |
| RR-06 | Intent | Pilot | Business | Are the pilot sites (Riverside, Hillcrest) formally agreed? | Executive minutes | Executive minutes, September | Neha Sharma | Dr. Anjali Rao | Met — executive minutes, September (v0.9 #2). |
| RR-07 | Intent | Pilot | Business | Are pilot success and stop criteria written and approved (under-triage limit, nurse response times, conditions to switch off auto-routing)? | Signed pilot criteria document | Programme repository; Go/No-Go minutes | Neha Sharma | Dr. Anjali Rao | Not met — no success or stop criteria exist in v0.9 or the evidence pack. |
| RR-08 | Intent | Pilot | Governance | Are risks from the October scope (automated replies, nurse capacity, mixed language) recorded in the enterprise risk register under AIP-2? | Register entries with owner and review date | Enterprise risk register | Owen Fletcher | Dr. Helen Mathews | Not met — only R-17 is evidenced in the register (E4 7 Dec); no entries for auto-replies or nurse capacity are shown. |
| RR-09 | Spec | Pilot | Technical | Has the architecture been reviewed for portal messages, automated replies and MedLink data flows added after ADR-009? | Architecture review addendum to ADR-009 | Architecture decision records | Imran Qureshi | Rahul Menon | Not met — ADR-009 is dated 21 Sept; scope changed 9 Oct; no later review (E8 item 4). |
| RR-10 | Spec | Pilot | Governance | Is there a Kestrel clinical safety case and hazard log, signed by the Kestrel CSO, covering automated replies, mixed-language messages and nurse-queue capacity (CSS-1)? | Signed Kestrel safety case and hazard log; Corvid log referenced as input | Clinical safety file | Dr. Helen Mathews | Dr. Anjali Rao | Not met — hazard log v2 is Corvid's, signed by Corvid's CSO, with none of those hazards; Dr. Mathews has not been asked to review it (E7). |
| RR-11 | Spec | Pilot | Quality | Does the test strategy set acceptance criteria for under-triage overall and per language group? | Approved test strategy | QA repository | Victor Osei | Dr. Helen Mathews | Not met — no acceptance criteria for under-triage are evidenced; regression suite excludes the model evaluation set (E4 27 Nov). |
| RR-12 | Spec | Pilot | Governance | Is a DPIA addendum covering portal messages and automated replies approved before patient messages are processed? | Approved DPIA addendum | DPIA register | Neha Sharma | Grace Liu | Not met — DPIA v1 covers referral letters only; the DPO has asked for an addendum (E4 2 Dec). |
| RR-13 | Plan | Pilot | Technical | Do plans exist for all 11 features, including automated reply drafting and threshold tuning, each with a clinical review step? | 11 of 11 feature plans | beacon/plans/ | Imran Qureshi | Dr. Helen Mathews | Not met — 9 of 11 plans; the two missing are auto-reply drafting and threshold tuning (A5). |
| RR-14 | Plan | Pilot | Governance | Are vendor contracts and data-processing agreements signed, with India data residency? | Signed contracts and DPAs | Contract register: CTR-311, CTR-312 | Neha Sharma | Grace Liu | Met — CTR-311 (Corvid) and CTR-312 (MedLink), both DPAs include India data residency (v0.9 #5). |
| RR-15 | Plan | Pilot | Technical | Is Beacon pinned to the evaluated model version instead of the floating alias corvid-med-latest, with the pinned-version cost approved? | triage-config.yaml showing a pinned version; approved cost change to CTR-311 | beacon/triage-config.yaml; contract register | Imran Qureshi | Marcus Bell | Not met — config uses corvid-med-latest (E3), which moves to corvid-med-3.3 on 15 Dec (E4 30 Nov); Kestrel chose the alias (E8 CTR-311 cl. 9.4). |
| RR-16 | Plan | Pilot | Operational | Does a nurse-capacity plan show the urgent-response target can be met at the 7–10 pm peak at both pilot sites? | Staffing calculation and rota | Nursing rota; programme repository | Priyanka Das | Dr. Anjali Rao | Not met — 2 night nurses who also cover the ward phone need ~75 minutes for the peak vs a 30-minute target (E4 1 Dec). |
| RR-17 | Build | Pilot | Technical | Is the code complete and merged, with the release candidate identified? | Release candidate build number | CI system; repository | Imran Qureshi | Victor Osei | Met — build 1.4.2, 87 PRs merged (A5). |
| RR-18 | Build | Pilot | Quality | Is the code regression suite green on the release candidate? | CI run on release build | CI system | Imran Qureshi | Victor Osei | Met — CI #2291 green on 1.4.2, 27 Nov (E4). Covers code only; the model evaluation is covered by RR-19. |
| RR-19 | Build | Pilot | Quality | Has the Kestrel model evaluation been re-run on the exact release configuration (build, model version, prompt version, threshold), and is it part of the release test suite? | Evaluation report naming build, model, prompt and threshold | Evaluation register; CI system | Dr. Farah Siddiqui | Victor Osei | Not met — ev-118 ran on build 1.4.0, corvid-med-3.2, threshold 0.80; the release is 1.4.2, floating alias, 0.72 (E1, E3). |
| RR-20 | Build | Pilot | Quality | Is under-triage on the release configuration within the CSO-approved limit overall and for mixed-language messages, or are all mixed-language messages routed to nurses? | Evaluation results by language group; routing rule test | Evaluation register | Dr. Farah Siddiqui | Dr. Helen Mathews | Not met — mixed-language under-triage 6.8% vs 1.6% English-only (E1); no limit has been approved and no routing rule exists. |
| RR-21 | Build | Pilot | Governance | Does change control block any model, prompt or threshold change until it is re-evaluated on Kestrel data and approved by the CSO (AIP-2)? | Change-control procedure; repository protection on triage-config.yaml | Change log; repository settings | Imran Qureshi | Dr. Helen Mathews | Not met — threshold changed on 25 Nov without re-evaluation or approval (E3, E4); v0.9 appendix lets Engineering tune it. |
| RR-22 | Build | Pilot | Operational | Does the audit log record, for every decision: input reference, category, confidence, rationale, model version, prompt version, threshold, route taken, reply text sent and nurse override? | log_fields in config; sample log entry | beacon/triage-config.yaml; log store | Kavya Nair | Owen Fletcher | Not met — log_fields records only message_id, category and confidence (E3). |
| RR-23 | Build | Pilot | Governance | Are patient messages and decision records retained for 8 years (RP-1)? | retention setting in config | beacon/triage-config.yaml | Kavya Nair | Grace Liu | Not met — retention_days is 365 (E3). |
| RR-24 | Review | Pilot | Technical | Has the release build passed penetration testing with all critical findings fixed and retested? | Penetration test and retest report, signed | Security test register: PT-2026-77 | Imran Qureshi | Rahul Menon | Met — PT-2026-77: 1 critical finding fixed, retest passed 30 Nov, signed R. Menon (v0.9 #13). |
| RR-25 | Review | Pilot | Technical | Has every PR been approved by a human who did not write the prompts that produced it? | Review record for each PR, incl. re-review of the 12 self-approved PRs | Repository PR history | Imran Qureshi | Victor Osei | Not met — 12 PRs were approved by I. Qureshi, who wrote their prompts (A5). |
| RR-26 | Review | Pilot | Governance | Is R-17 (mixed-language under-triage) either mitigated, or accepted in writing by the CMO or CSO with a review date (AIP-2)? | Mitigation evidence or signed acceptance with review date | Enterprise risk register | Owen Fletcher | Dr. Helen Mathews | Not met — R-17 was "accepted" by N. Sharma on behalf of delivery (E4 5 Dec, 7 Dec); she has no authority under AIP-2. |
| RR-27 | Review | Pilot | Quality | Do automated self-care replies read at grade 8 or below, in English, Hindi and Marathi (PCS-3)? | Reading-level and language test of a reply sample | QA repository | Dr. Farah Siddiqui | Dr. Helen Mathews | Not met — sampled replies read at grade 11 (E1); no Hindi or Marathi replies are evidenced. |
| RR-28 | Review | Pilot | Governance | Is AI-disclosure wording approved in English, Hindi and Marathi and included in every automated reply (PCS-3)? | Approved wording; sample reply | Communications approvals; reply templates | Neha Sharma | Owen Fletcher | Not met — draft with Legal, English only (E8 item 26). |
| RR-29 | Review | Pilot | Technical | Does the system meet latency targets at 3× pilot volume? | Load test report | Test register: LT-1.4.2 | Kavya Nair | Imran Qureshi | Met — LT-1.4.2, 1 Dec: p95 1.8 s at 3× pilot volume (v0.9 #15). Owner moved from T. Grant, who leaves 18 Dec. |
| RR-30 | Review | Pilot | Quality | Have patient-facing automated replies had an accessibility review? | Accessibility review report | QA repository | Neha Sharma | Victor Osei | Not met — marked N/A as a "backend service" (v0.9 #16), although Beacon writes to patients. |
| RR-31 | Deploy | Pilot | Operational | Has rollback been rehearsed for the application, model version, prompt version and threshold, plus a kill switch sending every message to manual nurse triage? | Rehearsal record for each element | Runbook §5; rehearsal log | Kavya Nair | Priyanka Das | Partly met — application rollback 1.4.2 → 1.3.9 in 4 minutes, 20 Nov (E6); model, prompt and kill switch are not covered. |
| RR-32 | Deploy | Pilot | Operational | Have 100% of pilot-site triage nurses completed Beacon training? | Learning-system completion report | Learning system | Priyanka Das | Kavya Nair | Not met — 11 of 29 (38%) completed, 7 Dec (E8 item 24). |
| RR-33 | Deploy | Pilot | Operational | Do patient replies to Beacon messages (e.g. "it's getting worse") reach the nurse queue, tested end to end, and does the contact centre have call scripts with an escalation route? | End-to-end routing test; issued call scripts | Test log; contact-centre procedures | Sunil Bhat | Priyanka Das | Not met — such replies land in the general inbox, answered within 48 hours (E4 3 Dec); only release notes were emailed, no scripts (E8 item 25). |
| RR-34 | Deploy | Pilot | Technical | Has Tobias Grant's handover to Imran Qureshi been recorded before 18 Dec (architecture, load test, rollback)? | Signed handover record | Programme repository | Imran Qureshi | Kavya Nair | Not started — v0.9 says technical items are Tobias's "until handover"; no handover record exists (A3). |
| RR-35 | Deploy | Pilot | Business | Is the pilot Go/No-Go decision recorded, with every open condition named, owned and dated? | Go/No-Go minutes | Executive minutes | Neha Sharma | Dr. Anjali Rao | Not started — meeting is 10 Dec; v0.9 calls it "a formality" (v0.9 #30). |
| RR-36 | Deploy | Network | Quality | Do clinician sampling results from the pilot show under-triage within the approved limit at both sites? | Weekly sampling reports | Clinical safety file | Priyanka Das | Dr. Helen Mathews | Not due — Network gate; note that no sampling is scheduled yet (E5). |
| RR-37 | Review | Network | Technical | Does a load test at nine-hospital volume meet latency targets? | Load test report at network volume | Test register | Kavya Nair | Imran Qureshi | Not met — the only test is at 3× pilot volume (v0.9 #15). |
| RR-38 | Plan | Network | Operational | Is there a staffing, training and on-call plan for all nine hospitals, revised using pilot data? | Network rollout plan v3 with per-site capacity | Programme repository | Priyanka Das | Kavya Nair | Not started — Rollout plan v2 predates any pilot evidence (v0.9 #28). |
| RR-39 | Review | Network | Governance | Is the safety case updated with pilot incidents, and has any model change (e.g. corvid-med-3.3) been re-evaluated and approved by the CSO? | Updated safety case; re-evaluation report and CSO approval | Clinical safety file; evaluation register | Dr. Helen Mathews | Dr. Anjali Rao | Not due — Network gate. |
| RR-40 | Deploy | Network | Business | Has the sponsor taken a separate network Go/No-Go on a pilot results report, with budget for a pinned model across nine sites confirmed? | Network Go/No-Go minutes; pilot results report; budget approval | Executive minutes | Marcus Bell | Dr. Anjali Rao | Not started — the v0.9 appendix makes the network rollout automatic after the pilot gate. |

Status summary (40 criteria, 35 Pilot, 5 Network): Met 7 · Partly met 1 · Not met 26 · Not started 4 · Not due 2.

Status key: Met = the evidence pack shows it is met; Partly met = some evidence, gap stated; Not met = evidence contradicts or is missing; Not started = no work evidenced on a required item; Not due = Network-gate item not yet assessable. Team-channel statements are treated as claims, not evidence.

# Part 5 · Readiness statement to the sponsor (M4, Day 3)

No more than half a page, addressed to Priya Raman. Write it so that it could be forwarded to the regulator unchanged.

| Heading | Your text |
| --- | --- |
| To | Dr. Anjali Rao, Chief Medical Officer and Programme Sponsor · From: AI Technical Program Manager, Beacon · 8 December 2026 · Basis: Release-Readiness Checklist v1 (40 criteria: 7 Met, 1 Partly met, 26 Not met, 4 Not started, 2 Not due) |
| Decision for 14 December | No-go for 14 December in the planned configuration (automatic routing and automated replies switched on). It becomes a Go at a re-convened Go/No-Go on the first date all ten conditions below are Met. |
| What is ready | Business case and pilot sites approved; contracts and DPAs with India data residency signed (CTR-311, CTR-312); build 1.4.2 complete with code regression green (CI #2291); penetration test passed with retest signed by Rahul Menon (PT-2026-77); load test passed at 3× pilot volume (LT-1.4.2); application rollback rehearsed in 4 minutes. |
| What is not ready | No Kestrel clinical safety case: the signed hazard log is Corvid's and Dr. Helen Mathews has not reviewed it (CSS-1). The system going live is not the one evaluated: threshold lowered to 0.72 without re-evaluation or CSO approval, and the floating model alias moves to corvid-med-3.3 on 15 Dec (AIP-2). Mixed-language under-triage is 6.8% vs 1.6%, and R-17 was accepted by someone without authority. Night nurses need ~75 minutes for the urgent peak against a 30-minute target, and only 11 of 29 are trained. Patient replies saying "it's getting worse" wait up to 48 hours. No under-triage monitoring and no paged responder. DPIA does not cover portal messages. Replies read at grade 11, English only, with disclosure unapproved. Logs miss key fields; retention is 365 days, not 8 years. |
| What would make it a yes (Pilot gate, before go-live) | 1. Spec/Review: Kestrel safety case and hazard log signed by Dr. Helen Mathews (RR-10). 2. Build: threshold set to 0.80, or the value in use, re-evaluated on the release configuration and approved by the CSO (AI-01, RR-19, RR-21): Dr. Farah Siddiqui. 3. Plan: model pinned to the evaluated version (RR-15): Imran Qureshi; cost approved by Marcus Bell. 4. Review: all mixed-language messages routed to nurses, or R-17 accepted in writing by you or the CSO with a review date (RR-26). 5. Plan/Deploy: night staffing meets the urgent target, and 100% of pilot nurses trained (AI-02, RR-16, RR-32): Priyanka Das. 6. Deploy: patient follow-up replies reach the nurse queue, tested end to end, and contact-centre scripts issued (RR-33): Sunil Bhat. 7. Deploy: drift monitor on a Kestrel baseline, paged to the on-call rota, with clinician sampling scheduled (AI-03): Kavya Nair. 8. Spec: DPIA addendum approved by Grace Liu (RR-12). 9. Review: replies at grade 8 or below in English, Hindi and Marathi, with disclosure approved (RR-27, RR-28). If not met, the pilot may start with automated replies switched off. 10. Build/Deploy: full audit fields, 8-year retention, and kill switch to manual triage rehearsed (RR-22, RR-23, RR-31): Kavya Nair. |
| What must be true before 11 January (Network gate) | A separate network Go/No-Go chaired by you, not automatic (RR-40). It requires: pilot clinician sampling showing under-triage within the CSO limit (RR-36); a load test at nine-hospital volume (RR-37); staffing, training and on-call plans per site (RR-38); the safety case updated with pilot incidents and any model change re-evaluated (RR-39); and Tobias Grant's handover recorded before 18 Dec (RR-34). If the pilot starts late, 11 January moves with it. |
| My recommendation, and why | Do not start on 14 December as planned. Today no one with authority under CSS-1 or AIP-2 has accepted Beacon's clinical risk; the configuration that would go live has never been evaluated; and the human safety net cannot absorb what Beacon would send it. The board announcement is a reason to move fast on the ten conditions, not a reason to waive them. A short delay is recoverable; an urgent patient sent self-care advice is not. |

# Part 6 · Assumptions

Proposed figures (A1–A3) become binding only when approved by Dr. Helen Mathews, Clinical Safety Officer.

| # | What I assumed | Why I needed to assume it |
| --- | --- | --- |
| A1 | The confidence threshold stays at 0.80 for the pilot (AI-01) until a re-evaluation on the release configuration and CSO approval set a different value. | 0.80 is the only value evaluated on Kestrel data (ev-118); the live 0.72 was never evaluated, and the case gives no CSO-approved value. |
| A2 | Human-in-the-loop time limits of 15 minutes for Emergency and 30 minutes for Urgent, with any breach escalated to the Head of Nursing (AI-02). These are proposed values for Dr. Helen Mathews to approve. | The case states only the v0.9 claim of "30-minute response" for urgent cases, and no Emergency limit or escalation route. |
| A3 | Drift-monitor bands (AI-03): under-triage no worse than the evaluated 2.1%; auto-route rate within ±5 points of the 69% baseline; any category's share within ±5 points; auto-routing switched off within 1 hour of a breach. All are proposals for CSO approval. | The case gives baseline figures (E1) but no tolerance, alert threshold or response time for drift. |
| A4 | Beacon can identify mixed-language or transliterated messages reliably enough to route them all to nurses (R-17 mitigation in AI-02 and RR-26). | ev-118 reports results for this group (n = 240), but the case does not say whether Beacon detects language mix at run time. |
| A5 | Kavya Nair's platform on-call rota can be extended to page Beacon clinical-drift alerts, not only infrastructure alerts. | E5 says the rota is paged only for latency, errors and outages; the case does not say whether it can carry other alerts. |
| A6 | Kestrel can buy a pinned model version (corvid-med-3.2) under CTR-311 and switch to it before Corvid moves the alias on 15 Dec (RR-15). | E8 says pinned versions are available at additional cost but gives no lead time or price. |
| A7 | Setting auto_reply_enabled to false turns off automated replies without a code change, so the pilot could start with replies off as a fallback (readiness statement, condition 9). | E3 shows the flag exists, but the case does not confirm its effect or that it was tested. |
| A8 | Message volume scales roughly with the number of hospitals, so nine hospitals exceed 3× the two-site pilot volume (RR-37). | The case gives no volume figures; LT-1.4.2 is stated only relative to pilot volume. |
| A9 | Tobias Grant can carry out the architecture handover and the independent re-review of the 12 self-approved PRs before 18 Dec, as Responsible only (3a, RR-25, RR-34). | He is still employed until 18 Dec, but the case does not say how much of his remaining time is available. |
| A10 | Neha Sharma prepares the DPIA addendum, AI-disclosure wording and accessibility review, with Grace Liu, Owen Fletcher and Victor Osei approving (RR-12, RR-28, RR-30). | These sit with the Communications and Legal teams, which are not named people; A3 gives no individual owner, so the Delivery Lead was the only assignable person. |
| A11 | The enterprise risk register holds no entries for automated replies or nurse-queue capacity (RR-08). | The evidence shows only R-17; the full register was not provided. |
| A12 | The workbook's five dimensions (Business, Technical, Quality, Governance, Operational) are the Week 1 dimensions. The Findings Log categories Clinical, Data & Security and Compliance map to Quality, Technical and Governance. | The case pack refers to "five dimensions" without naming them; the names come from the workbook template for Part 3. |
| A13 | The Network gate needs pilot clinician-sampling data, so if the pilot starts after 14 Dec, the 11 Jan date moves by the same amount. | The case sets both dates but states no minimum pilot duration. |

Peer Review · Rubric Scorecard — Beacon Release-Readiness Checklist v1

Kestrel Health Network · Beacon AI-assisted patient triage · Status as of 8 December 2026 · Pilot gate 14 Dec 2026 · Network gate 11 Jan 2027

1. Review header

| Field | Entry |
| --- | --- |
| Document under review | Beacon_Release_Readiness_Checklist_v1.docx: 4a header block and 4b criteria (40 rows: AI-01 to AI-03, RR-04 to RR-40), status as of 8 December 2026 |
| Cross-reference baseline | Beacon_Findings_Log.docx (F1–F20) and the Kestrel / Beacon case pack (A3, A4, A5, Part B v0.9, E1–E8) |
| Review type | Week 1 Peer Review Sheet: three core skills (0/25/50/75/100) and the Trust & Governance Design competency (Level 1–5) |
| Governing rules | Rule 1: score only what can be quoted; if not found, score 0 and record where you looked. Rule 2: do not score polish, formatting or length. |
| Completion rule | PASS = named individual owner + completed control + current verifiable evidence + evidence location + required approval. A basis resting only on a v0.9 note or a team-channel message is not PASS. |
| Reviewer · date | [reviewer candidate id] · 8 December 2026 |

2. Rubric scorecard

Each score is backed by a quote (criterion ID, column) or by "not found" with the locations searched.

| Rubric line | Score | Supporting evidence quoted from checklist | Gap preventing the next score level |
| --- | --- | --- | --- |
| Skill 1 – Governance Workflow Design | 100/100 | 4a, Accountable owners by dimension: “Business: Dr. Anjali Rao · Technical: Imran Qureshi · Quality: Victor Osei · Governance: Dr. Helen Mathews · Operational: Kavya Nair.” All five dimensions appear in 4b. Every supplied row uses the matching dimension Accountable, names an individual approver and avoids owner self-approval. | All stated controls are present. Document-control exception: the supplied checklist contains 35 criteria, ending at RR-35, rather than the stated 40 ending at RR-40. |
| Skill 2 – AI Governance Policy Design | 75/100 | AI-01, Criterion: “confidence ≥0.72… justified by a Kestrel-data evaluation of build 1.4.2… scores below 0.72 sent to the triage-nurse queue.” AI-02 lists six HITL triggers, a triage nurse and 30 minutes. AI-03 requires category distribution, mean confidence, clinician-sampled under-triage, a Kestrel baseline, a two-percentage-point band, paging, a named responder and stopping auto-routing. | AI-03 does not quantify clinician sample size or cadence and provides no actual Kestrel baseline value. AI-01’s status shows 0.72 is unapproved, but the criterion does not explicitly label the number as proposed. |
| Skill 3 – Stage-Gate & Artefact-Chain Literacy | 75/100 | Every supplied 4b row contains Stage and Phase; all six stages are used. RR-30 to RR-35 are Network rows. RR-35 requires a “separate signed Network Go/No-Go record.” RR-17 identifies build 1.4.2, pinned model, release prompt and threshold 0.72. | RR-35 does not require evidence that preceding Network gates have passed. RR-22 and RR-23 do not link penetration and load tests to the same build, model, prompt and threshold, and no row carries the complete identifier through staging and production. |
| Competency – Trust & Governance Design | Level 4 of 5 | Every supplied row names Evidence required, Where logged, an Accountable owner, an Approver and a status basis. Material controls such as AI-01, AI-02, AI-03, RR-17, RR-19, RR-20, RR-24 and RR-25 are honestly marked Not met. | Five Met rows do not satisfy the completion rule because their bases cite v0.9 notes or a team-channel statement rather than completed current evidence at the named location. End-to-end release provenance is incomplete. |

# Before you submit

Tick each box only if it is true. Every "no" is a mark you can still recover. The full self-review is in the Lab Kit, Section 10.

| Check | Done? |
| --- | --- |
| Part 1: the cover block is complete | ☐ |
| Part 2: 12 or more findings, covering all five dimensions; the example row is deleted | ☐ |
| Part 3: one named Accountable person for each dimension; no teams, no "TBD" | ☐ |
| Part 4: three separate AI-control rows (AI-01, AI-02, AI-03) with every field | ☐ |
| Part 4: every row has a stage, and all six stages are used | ☐ |
| Part 4: every row names its evidence and where it is logged | ☐ |
| Part 4: statuses match the evidence; "Not met" appears where the evidence says so | ☐ |
| Part 4: the header says the Go/No-Go confirms gates already passed | ☐ |
| Part 5: the readiness statement is written, in half a page or less | ☐ |
| Nothing important is only in an image or only in your head | ☐ |

Submit this file through the submission process your facilitator gives you. You have up to three attempts.